## Sheet1
Working on | Hours | Date | Total Hours | 132.25
AI Reasearch | 2 | 2014-09-29 | Week 1 Hours | 37.5
Neural NetWork Code | 2 | 2014-09-29 | Week 2 Hours | 42
Neural NetWork Code | 1 | 2014-09-30 | Week 3 Hours | 44
Reasearching Number Patterns | 2 | 2014-09-30
Working on Brain class | 3 | 2014-10-01
Save and Loading Brain | 1 | 2014-10-02
Cleaned Brain and added a new pattern | 2 | 2014-10-02
Planing out Brain fully and PathFinder | 3 | 2014-10-03
Adding new Patterns/Fixing old ones | 3 | 2014-10-04
Created Sized List class | 1 | 2014-10-04
Added more paterns, fixed bugs, new functionality for AI | 3 | 2014-10-04
Test Brain to make sure it works on own with random numbers | 1 | 2014-10-04
Research and look at old code for PathFinding | 2.5 | 2014-10-05
Wrote PathFinder & used unity testing with it | 4 | 2014-10-05
Made an AI that used PathFinder with Brain to function | 2 | 2014-10-05
Updated GUI to use The new AI instead of the Brain with random numbers | 2 | 2014-10-06
Tested and Tweaked PathFinder and killed bugs | 2 | 2014-10-06
Tested and Tweaked AI with Brain interacting with PathFinder | 1 | 2014-10-06
Created three test graphs | 1 | 2014-10-07
Tested AI with the new graphs used | 2 | 2014-10-07
Made new project for The acutal game to use built Ai | 0.5 | 2014-10-07
Found free Builder from Unity store and learned how to use it | 2 | 2014-10-07
Made starting rooms/hallways for maze | 2 | 2014-10-08
Making rooms/hallways etc as need while building a Maze for graph1 image | 5 | 2014-10-08
Finished the Maze(Graph1) | 1 | 2014-10-09
Created Node and NodeManager scripts and prefabs | 2 | 2014-10-09
Created PathChoice and updated Nodes | 1.5 | 2014-10-09
Placed Nodes and PathChoice objects in the maze | 0.5 | 2014-10-09
Tested Maze | 0.5 | 2014-10-09
Made Sound Manager & MovementSoundManager | 0.5 | 2014-10-09
Found footstep noise and put in game with player movement | 0.5 | 2014-10-09
Making Reset Button | 0.5 | 2014-10-09
Getting Reset Button to reset player and all nodes and pathways | 2 | 2014-10-10
Converting AI and Game to use GUI Nodes and paths for game | 3 | 2014-10-10
Converting AI and Game to use GUI Nodes and paths for game | 3 | 2014-10-11
Testing Unity Maze with AI, fixing bugs, fixing AI learning | 1.5 | 2014-10-11
Writing Simple Ai Script | 0.5 | 2014-10-12
Recording Simple Ai Script | 1.5 | 2014-10-12
Getting Simple Ai Script into the game. | 4 | 2014-10-12
Testing for Errors, Adding in Neutrality | 2 | 2014-10-12
Researching Random generation for mazes | 2 | 2014-10-13
Writing Story(prequel) | 3 | 2014-10-13
Fix movement sounds | 2.5 | 2014-10-14
updating prefabs with nodes and pathchoices | 0.5 | 2014-10-14
Write Maze ending types(events that will happen and how they affect game) | 2 | 2014-10-15
finding models | 1 | 2014-10-15
finding models | 4 | 2014-10-16
seting up models (textures, collision, scale, etc) | 2.5 | 2014-10-16
seting up models (textures, collision, scale, etc) | 4.5 | 2014-10-17
Drawing new map | 2 | 2014-10-17
Drawing new map (Finished) | 2 | 2014-10-18
Designing new Node Travel | 1 | 2014-10-19
Making new Prefabs, Switching to code graph based instead of GUI | 7 | 2014-10-19
Fixing Errors in new setup | 2.5 | 2014-10-19
Fixed teleporting lag/glitch | 2 | 2014-10-19
Working on spawning Objects at end of the maze | 3 | 2014-10-20
Working on spawning Objects at end of the maze | 3.5 | 2014-10-20
Working on spawning Objects at end of the maze | 3 | 2014-10-20
Fixing Bugs/Cleaning a bit of code | 1 | 2014-10-20
Research UI in Unity 4.6 & update to 4.6 | 1 | 2014-10-21
Research UI in Unity 4.6/Making Demo Menu | 7.75 | 2014-10-22