## Sheet1
Working on | Hours | Date | Total Hours | 72.5
AI Reasearch | 2 | 2014-09-29 | Week 1 Hours | 37.5
Neural NetWork Code | 2 | 2014-09-29
Neural NetWork Code | 1 | 2014-09-30
Reasearching Number Patterns | 2 | 2014-09-30
Working on Brain class | 3 | 2014-10-01
Save and Loading Brain | 1 | 2014-10-02
Cleaned Brain and added a new pattern | 2 | 2014-10-02
Planing out Brain fully and PathFinder | 3 | 2014-10-03
Adding new Patterns/Fixing old ones | 3 | 2014-10-04
Created Sized List class | 1 | 2014-10-04
Added more paterns, fixed bugs, new functionality for AI | 3 | 2014-10-04
Test Brain to make sure it works on own with random numbers | 1 | 2014-10-04
Research and look at old code for PathFinding | 2.5 | 2014-10-05
Wrote PathFinder & used unity testing with it | 4 | 2014-10-05
Made an AI that used PathFinder with Brain to function | 2 | 2014-10-05
Updated GUI to use The new AI instead of the Brain with random numbers | 2 | 2014-10-06
Tested and Tweaked PathFinder and killed bugs | 2 | 2014-10-06
Tested and Tweaked AI with Brain interacting with PathFinder | 1 | 2014-10-06
Created three test graphs | 1 | 2014-10-07
Tested AI with the new graphs used | 2 | 2014-10-07
Made new project for The acutal game to use built Ai | 0.5 | 2014-10-07
Found free Builder from Unity store and learned how to use it | 2 | 2014-10-07
Made starting rooms/hallways for maze | 2 | 2014-10-08
Making rooms/hallways etc as need while building a Maze for graph1 image | 5 | 2014-10-08
Finished the Maze(Graph1) | 1 | 2014-10-09
Created Node and NodeManager scripts and prefabs | 2 | 2014-10-09
Created PathChoice and updated Nodes | 1.5 | 2014-10-09
Placed Nodes and PathChoice objects in the maze | 0.5 | 2014-10-09
Tested Maze | 0.5 | 2014-10-09
Made Sound Manager & MovementSoundManager | 0.5 | 2014-10-09
Found footstep noise and put in game with player movement | 0.5 | 2014-10-09
Making Reset Button | 0.5 | 2014-10-09
Getting Reset Button to reset player and all nodes and pathways | 2 | 2014-10-10
Converting AI and Game to use GUI Nodes and paths for game | 3 | 2014-10-10
Converting AI and Game to use GUI Nodes and paths for game | 3 | 2014-10-11
Testing Unity Maze with AI, fixing bugs, fixing AI learning | 1.5 | 2014-10-11
Writing Simple Ai Script | 0.5 | 2014-10-14
Recording Simple Ai Script | 1.5 | 2014-10-14
Getting Simple Ai Script into the game. | 4 | 2014-10-14